## Jira Import
Issue ID | Project Key | Summary | Issue Type | Parent | Status | WBS Level | Process Phase | Blocks Issue IDs | Link Type
1 | ABC | Infrastructure Platform | Epic | ABC-123 | Backlog | Epic / System | 2. Infrastructure Setup
2 | ABC | Deploy OpenMetadata Stack | Task | 1 | Backlog | Task / Deliverable | 2. Infrastructure Setup | 6, 10 | blocks
3 | ABC | Setup Docker Compose | Sub-task | 2 | Backlog | Sub-task / Work Unit | 2. Infrastructure Setup
4 | ABC | Configure OpenMetadata service | Sub-task | 2 | Backlog | Sub-task / Work Unit | 2. Infrastructure Setup
5 | ABC | Configure dependencies | Sub-task | 2 | Backlog | Sub-task / Work Unit | 2. Infrastructure Setup
6 | ABC | Setup Database Layer | Task | 1 | Backlog | Task / Deliverable | 2. Infrastructure Setup | 15, 44 | blocks
7 | ABC | Create databases | Sub-task | 6 | Backlog | Sub-task / Work Unit | 2. Infrastructure Setup
8 | ABC | Seed data | Sub-task | 6 | Backlog | Sub-task / Work Unit | 2. Infrastructure Setup
9 | ABC | Define schemas | Sub-task | 6 | Backlog | Sub-task / Work Unit | 2. Infrastructure Setup
10 | ABC | Configure Networking | Task | 1 | Backlog | Task / Deliverable | 2. Infrastructure Setup | 15 | blocks
11 | ABC | Setup ports | Sub-task | 10 | Backlog | Sub-task / Work Unit | 2. Infrastructure Setup
12 | ABC | Validate UI | Sub-task | 10 | Backlog | Sub-task / Work Unit | 2. Infrastructure Setup
13 | ABC | Configure connectivity | Sub-task | 10 | Backlog | Sub-task / Work Unit | 2. Infrastructure Setup
14 | ABC | Metadata Ingestion System | Epic | ABC-123 | Backlog | Epic / System | 3. Metadata Ingestion
15 | ABC | Define Data Sources | Task | 14 | Backlog | Task / Deliverable | 3. Metadata Ingestion | 18 | blocks
16 | ABC | Identify systems | Sub-task | 15 | Backlog | Sub-task / Work Unit | 3. Metadata Ingestion
17 | ABC | Define ingestion scope | Sub-task | 15 | Backlog | Sub-task / Work Unit | 3. Metadata Ingestion
18 | ABC | Build Ingestion Pipelines | Task | 14 | Backlog | Task / Deliverable | 3. Metadata Ingestion | 22, 57 | blocks
19 | ABC | Create configs | Sub-task | 18 | Backlog | Sub-task / Work Unit | 3. Metadata Ingestion
20 | ABC | Schedule ingestion | Sub-task | 18 | Backlog | Sub-task / Work Unit | 3. Metadata Ingestion
21 | ABC | Validate runs | Sub-task | 18 | Backlog | Sub-task / Work Unit | 3. Metadata Ingestion
22 | ABC | Validate Metadata | Task | 14 | Backlog | Task / Deliverable | 3. Metadata Ingestion | 79, 92 | blocks
23 | ABC | Verify schemas | Sub-task | 22 | Backlog | Sub-task / Work Unit | 3. Metadata Ingestion
24 | ABC | Check lineage | Sub-task | 22 | Backlog | Sub-task / Work Unit | 3. Metadata Ingestion
25 | ABC | Validate extraction | Sub-task | 22 | Backlog | Sub-task / Work Unit | 3. Metadata Ingestion
26 | ABC | Governance System | Epic | ABC-123 | Backlog | Epic / System | 4. Data Governance Setup
27 | ABC | Define Policies | Task | 26 | Backlog | Task / Deliverable | 4. Data Governance Setup | 31 | blocks
28 | ABC | Access control rules | Sub-task | 27 | Backlog | Sub-task / Work Unit | 4. Data Governance Setup
29 | ABC | Role mapping | Sub-task | 27 | Backlog | Sub-task / Work Unit | 4. Data Governance Setup
30 | ABC | Compliance alignment | Sub-task | 27 | Backlog | Sub-task / Work Unit | 4. Data Governance Setup
31 | ABC | Implement Metadata Governance | Task | 26 | Backlog | Task / Deliverable | 4. Data Governance Setup | 35, 83 | blocks
32 | ABC | Tagging | Sub-task | 31 | Backlog | Sub-task / Work Unit | 4. Data Governance Setup
33 | ABC | Ownership | Sub-task | 31 | Backlog | Sub-task / Work Unit | 4. Data Governance Setup
34 | ABC | Classification | Sub-task | 31 | Backlog | Sub-task / Work Unit | 4. Data Governance Setup
35 | ABC | Data Quality Integration | Task | 26 | Backlog | Task / Deliverable | 4. Data Governance Setup | 92 | blocks
36 | ABC | Define checks | Sub-task | 35 | Backlog | Sub-task / Work Unit | 4. Data Governance Setup
37 | ABC | Integrate Great Expectations | Sub-task | 35 | Backlog | Sub-task / Work Unit | 4. Data Governance Setup
38 | ABC | Store results | Sub-task | 35 | Backlog | Sub-task / Work Unit | 4. Data Governance Setup
39 | ABC | Data Contracts System | Epic | ABC-123 | Backlog | Epic / System | 5. Data Contracts & Validation
40 | ABC | Define Contracts | Task | 39 | Backlog | Task / Deliverable | 5. Data Contracts & Validation | 44, 27 | blocks
41 | ABC | Schema definitions | Sub-task | 40 | Backlog | Sub-task / Work Unit | 5. Data Contracts & Validation
42 | ABC | Constraints | Sub-task | 40 | Backlog | Sub-task / Work Unit | 5. Data Contracts & Validation
43 | ABC | Ownership metadata | Sub-task | 40 | Backlog | Sub-task / Work Unit | 5. Data Contracts & Validation
44 | ABC | Build Validation Engine | Task | 39 | Backlog | Task / Deliverable | 5. Data Contracts & Validation | 48 | blocks
45 | ABC | Python scripts | Sub-task | 44 | Backlog | Sub-task / Work Unit | 5. Data Contracts & Validation
46 | ABC | Enforcement logic | Sub-task | 44 | Backlog | Sub-task / Work Unit | 5. Data Contracts & Validation
47 | ABC | Error handling | Sub-task | 44 | Backlog | Sub-task / Work Unit | 5. Data Contracts & Validation
48 | ABC | CI/CD Integration | Task | 39 | Backlog | Task / Deliverable | 5. Data Contracts & Validation
49 | ABC | Trigger validation | Sub-task | 48 | Backlog | Sub-task / Work Unit | 5. Data Contracts & Validation
50 | ABC | Fail on violations | Sub-task | 48 | Backlog | Sub-task / Work Unit | 5. Data Contracts & Validation
51 | ABC | Publish results | Sub-task | 48 | Backlog | Sub-task / Work Unit | 5. Data Contracts & Validation
52 | ABC | Orchestration System (Dagster) | Epic | ABC-123 | Backlog | Epic / System | 6. Orchestration (Dagster Integration)
53 | ABC | Setup Dagster | Task | 52 | Backlog | Task / Deliverable | 6. Orchestration (Dagster Integration) | 57 | blocks
54 | ABC | Initialize repo | Sub-task | 53 | Backlog | Sub-task / Work Unit | 6. Orchestration (Dagster Integration)
55 | ABC | Configure jobs | Sub-task | 53 | Backlog | Sub-task / Work Unit | 6. Orchestration (Dagster Integration)
56 | ABC | Setup resources | Sub-task | 53 | Backlog | Sub-task / Work Unit | 6. Orchestration (Dagster Integration)
57 | ABC | Build ETL Pipelines | Task | 52 | Backlog | Task / Deliverable | 6. Orchestration (Dagster Integration) | 61 | blocks
58 | ABC | Extract | Sub-task | 57 | Backlog | Sub-task / Work Unit | 6. Orchestration (Dagster Integration)
59 | ABC | Transform | Sub-task | 57 | Backlog | Sub-task / Work Unit | 6. Orchestration (Dagster Integration)
60 | ABC | Load | Sub-task | 57 | Backlog | Sub-task / Work Unit | 6. Orchestration (Dagster Integration)
61 | ABC | Metadata Sync | Task | 52 | Backlog | Task / Deliverable | 6. Orchestration (Dagster Integration) | 66, 92 | blocks
62 | ABC | Trigger ingestion | Sub-task | 61 | Backlog | Sub-task / Work Unit | 6. Orchestration (Dagster Integration)
63 | ABC | Push lineage | Sub-task | 61 | Backlog | Sub-task / Work Unit | 6. Orchestration (Dagster Integration)
64 | ABC | Sync catalog | Sub-task | 61 | Backlog | Sub-task / Work Unit | 6. Orchestration (Dagster Integration)
65 | ABC | Observability & Lineage | Epic | ABC-123 | Backlog | Epic / System | 7. Lineage & Observability
66 | ABC | Enable Lineage | Task | 65 | Backlog | Task / Deliverable | 7. Lineage & Observability | 70 | blocks
67 | ABC | Configure sources | Sub-task | 66 | Backlog | Sub-task / Work Unit | 7. Lineage & Observability
68 | ABC | Validate lineage | Sub-task | 66 | Backlog | Sub-task / Work Unit | 7. Lineage & Observability
69 | ABC | Map transformations | Sub-task | 66 | Backlog | Sub-task / Work Unit | 7. Lineage & Observability
70 | ABC | Monitoring & Alerts | Task | 65 | Backlog | Task / Deliverable | 7. Lineage & Observability | 74 | blocks
71 | ABC | Setup alerts | Sub-task | 70 | Backlog | Sub-task / Work Unit | 7. Lineage & Observability
72 | ABC | Monitor jobs | Sub-task | 70 | Backlog | Sub-task / Work Unit | 7. Lineage & Observability
73 | ABC | Track quality | Sub-task | 70 | Backlog | Sub-task / Work Unit | 7. Lineage & Observability
74 | ABC | Logging | Task | 65 | Backlog | Task / Deliverable | 7. Lineage & Observability
75 | ABC | Capture logs | Sub-task | 74 | Backlog | Sub-task / Work Unit | 7. Lineage & Observability
76 | ABC | Store metadata | Sub-task | 74 | Backlog | Sub-task / Work Unit | 7. Lineage & Observability
77 | ABC | Analyze failures | Sub-task | 74 | Backlog | Sub-task / Work Unit | 7. Lineage & Observability
78 | ABC | User Experience & Validation | Epic | ABC-123 | Backlog | Epic / System | 8. UI & User Experience Validation
79 | ABC | UI Exploration | Task | 78 | Backlog | Task / Deliverable | 8. UI & User Experience Validation | 87 | blocks
80 | ABC | Search datasets | Sub-task | 79 | Backlog | Sub-task / Work Unit | 8. UI & User Experience Validation
81 | ABC | View schemas | Sub-task | 79 | Backlog | Sub-task / Work Unit | 8. UI & User Experience Validation
82 | ABC | Explore lineage | Sub-task | 79 | Backlog | Sub-task / Work Unit | 8. UI & User Experience Validation
83 | ABC | Role Testing | Task | 78 | Backlog | Task / Deliverable | 8. UI & User Experience Validation | 87 | blocks
84 | ABC | Validate permissions | Sub-task | 83 | Backlog | Sub-task / Work Unit | 8. UI & User Experience Validation
85 | ABC | Test workflows | Sub-task | 83 | Backlog | Sub-task / Work Unit | 8. UI & User Experience Validation
86 | ABC | Confirm governance | Sub-task | 83 | Backlog | Sub-task / Work Unit | 8. UI & User Experience Validation
87 | ABC | Feedback Loop | Task | 78 | Backlog | Task / Deliverable | 8. UI & User Experience Validation | 96 | blocks
88 | ABC | Collect feedback | Sub-task | 87 | Backlog | Sub-task / Work Unit | 8. UI & User Experience Validation
89 | ABC | Identify issues | Sub-task | 87 | Backlog | Sub-task / Work Unit | 8. UI & User Experience Validation
90 | ABC | Refine configs | Sub-task | 87 | Backlog | Sub-task / Work Unit | 8. UI & User Experience Validation
91 | ABC | Documentation & Evaluation | Epic | ABC-123 | Backlog | Epic / System | 9-10. Documentation / Evaluation
92 | ABC | Documentation | Task | 91 | Backlog | Task / Deliverable | 9-10. Documentation / Evaluation | 96 | blocks
93 | ABC | Architecture diagrams | Sub-task | 92 | Backlog | Sub-task / Work Unit | 9-10. Documentation / Evaluation
94 | ABC | Setup guides | Sub-task | 92 | Backlog | Sub-task / Work Unit | 9-10. Documentation / Evaluation
95 | ABC | Config documentation | Sub-task | 92 | Backlog | Sub-task / Work Unit | 9-10. Documentation / Evaluation
96 | ABC | Evaluation | Task | 91 | Backlog | Task / Deliverable | 9-10. Documentation / Evaluation | 100 | blocks
97 | ABC | Measure success | Sub-task | 96 | Backlog | Sub-task / Work Unit | 9-10. Documentation / Evaluation
98 | ABC | Identify gaps | Sub-task | 96 | Backlog | Sub-task / Work Unit | 9-10. Documentation / Evaluation
99 | ABC | Assess adoption | Sub-task | 96 | Backlog | Sub-task / Work Unit | 9-10. Documentation / Evaluation
100 | ABC | Roadmap Planning | Task | 91 | Backlog | Task / Deliverable | 9-10. Documentation / Evaluation
101 | ABC | Define production architecture | Sub-task | 100 | Backlog | Sub-task / Work Unit | 9-10. Documentation / Evaluation
102 | ABC | Plan scaling | Sub-task | 100 | Backlog | Sub-task / Work Unit | 9-10. Documentation / Evaluation
103 | ABC | Define next steps | Sub-task | 100 | Backlog | Sub-task / Work Unit | 9-10. Documentation / Evaluation

## Dependencies
Blocking Issue ID | Blocking Summary | Link Type | Blocked Issue ID | Blocked Summary | Process WBS Dependency Rationale
2 | Deploy OpenMetadata Stack | blocks | 6 | Setup Database Layer | Infrastructure environment must exist before database setup is validated.
2 | Deploy OpenMetadata Stack | blocks | 10 | Configure Networking | OpenMetadata services must be running before networking/access validation.
6 | Setup Database Layer | blocks | 15 | Define Data Sources | Data sources depend on available sample databases and schemas.
10 | Configure Networking | blocks | 15 | Define Data Sources | Service connectivity must exist before connecting source systems.
15 | Define Data Sources | blocks | 18 | Build Ingestion Pipelines | Ingestion pipelines require defined sources and scope.
18 | Build Ingestion Pipelines | blocks | 22 | Validate Metadata | Metadata validation requires at least one ingestion run.
27 | Define Policies | blocks | 31 | Implement Metadata Governance | Governance implementation requires policy definitions.
31 | Implement Metadata Governance | blocks | 35 | Data Quality Integration | Quality results should be tied to classifications/ownership.
40 | Define Contracts | blocks | 44 | Build Validation Engine | Validation scripts depend on contract definitions.
44 | Build Validation Engine | blocks | 48 | CI/CD Integration | CI/CD integration depends on validation logic.
53 | Setup Dagster | blocks | 57 | Build ETL Pipelines | ETL pipelines require Dagster project setup.
57 | Build ETL Pipelines | blocks | 61 | Metadata Sync | Metadata sync should run after ETL jobs exist.
61 | Metadata Sync | blocks | 66 | Enable Lineage | Lineage depends on metadata sync from orchestrated pipelines.
66 | Enable Lineage | blocks | 70 | Monitoring & Alerts | Monitoring needs lineage/metadata signals to observe.
70 | Monitoring & Alerts | blocks | 74 | Logging | Logging supports monitoring and failure analysis.
22 | Validate Metadata | blocks | 79 | UI Exploration | UI exploration needs ingested metadata to inspect.
31 | Implement Metadata Governance | blocks | 83 | Role Testing | Role testing depends on governance controls being configured.
79 | UI Exploration | blocks | 87 | Feedback Loop | Feedback loop follows catalog UI review.
83 | Role Testing | blocks | 87 | Feedback Loop | Feedback loop follows role and governance testing.
22 | Validate Metadata | blocks | 92 | Documentation | Technical documentation should reflect validated metadata behavior.
35 | Data Quality Integration | blocks | 92 | Documentation | Documentation should include quality integration results.
61 | Metadata Sync | blocks | 92 | Documentation | Documentation should include orchestration/metadata sync workflow.
87 | Feedback Loop | blocks | 96 | Evaluation | Evaluation should consider stakeholder feedback.
92 | Documentation | blocks | 96 | Evaluation | Evaluation uses documented implementation evidence.
96 | Evaluation | blocks | 100 | Roadmap Planning | Roadmap planning follows evaluation and gap analysis.
18 | Build Ingestion Pipelines | blocks | 57 | Build ETL Pipelines | ETL should align with ingestion pipeline scope.
40 | Define Contracts | blocks | 27 | Define Policies | Policies should reflect contract and ownership requirements.
6 | Setup Database Layer | blocks | 44 | Build Validation Engine | Validation needs sample schema/data targets.

## Import Notes
OpenMetadata PoC Jira Import Workbook
Purpose | System-based WBS is preserved as Jira hierarchy while process-WBS sequencing is represented as blocks dependencies.
Existing top parent issue | ABC-123
Project Key | ABC
Jira Import Mapping
Issue ID | Temporary import identifier generated in this workbook.
Project Key | Existing Jira project key. Change ABC if your Jira project key differs.
Parent | Epics point to existing parent ABC-123; tasks/sub-tasks point to temporary Issue IDs.
Status | All rows are set to Backlog.
Blocks Issue IDs | Comma-separated temporary issue IDs blocked by this row.
Link Type | Use blocks for blocker relationships.
Recommended import note | If Jira does not accept comma-separated links in one column, use the Dependencies sheet as an edge list and import/link dependencies separately.